## Dashboard
PIA Master Backlog Dashboard
Generated: 2026-05-27 14:35 ¦ Source of truth snapshot for project management
Metric | Value | Notes |  | Priority | Count | Category | Items
Total backlog items | 215 | All rows in Backlog sheet |  | P0 | 42 | Academy | 21
P0 items | 42 | Critical / foundational |  | P1 | 112 | Portfolio | 18
P1 items | 112 | High priority |  | P2 | 10 | Earnings | 13
Done / Approved | 7 | Delivered and approved |  |  |  | Integrations | 10
Tech Pass / UAT pending | 3 | Needs UAT |  |  |  | Markets & Macro | 10
Planned | 148 | Future work |  |  |  | Alerts | 9
New bugs/items | 3 | Newly captured |  |  |  | Backend | 9
|  |  |  | Status | Count | Mobile | 9
|  |  |  | DONE | 7 | Notes | 9
|  |  |  | FOUNDATION DONE | 1 | Workspace | 9
|  |  |  | TECH PASS | 3 | Scanner | 8
|  |  |  | IN PROGRESS | 1 | Backup | 7
|  |  |  | NEW | 3 | Command | 7
|  |  |  | PLANNED | 148 | Performance | 7
|  |  |  | ENVIRONMENT | 1 | Settings | 7
[6 empty] | AI Core | 6
[6 empty] | AI Infrastructure | 6
When | Action | Description | Priority |  |  | Crypto | 6
Now | Sprint 2B Mock Compliance | Athena: mobile-first Home mock compliance; Hermes: stock/news/videos mock compliance. | P0 |  |  | Discord | 6
Next | UAT after preview/local | UAT must be mock-compliance, not only load/no crash. | P0 |  |  | Trade Coach | 6
Next | Backlog/Git file update | Commit XLSX + markdown/JSON source-of-truth into repo. | P0 |  |  | Watchlists | 5
Later | Vercel mobile preview | Branch preview URLs for mobile UAT. | P0 |  |  | Bug | 4
Later | Portfolio V3 MVP | My Portfolio with snapshots, heatmap, attribution, targets, intelligence. | P0 |  |  | Voice | 4
[6 empty] | Foundation | 3
[6 empty] | Sources | 3
[6 empty] | DevOps | 2
[6 empty] | Stock Workspace | 2
[6 empty] | Change | 1
[6 empty] | Design System | 1
[6 empty] | Heatmap | 1
[6 empty] | News | 1
[6 empty] | Process | 1
[6 empty] | Stock Intelligence | 1
[6 empty] | UI/UX | 1
[6 empty] | UX | 1
[6 empty] | Widgets | 1
Route | Purpose | Validation Expectation
/ | Home dashboard and desktop workspace shell | Must load with no route regression; widgets must be clickable
/mobile | Mobile-first command experience | Polished, compact, readable, no horizontal overflow; swipe must work
/setup | Setup and onboarding flow | Must remain preserved
Priority | Area | Requirement
P0 | Home dashboard | Premium visual identity while preserving working widgets
P0 | Mobile Home | Must not feel like squeezed desktop
P0 | Privacy mode | Amount hiding must remain intact
P0 | Notifications | Mobile-safe Notification Center with grouped premium cards
P1 | Status dock | Surface IBKR, Yahoo, and Feeds status in compact shell UI
v0.3.15 | Workspace Manager + Custom Workspaces | Implemented 2026-05-28 | Mobile hamburger manager, direct overflow workspace open, Settings/About access, configurable pinned bottom nav, desktop sidebar parity, custom local workspaces.

## Backlog
ID | Category | Epic | Item | Description | Priority | Status | Owner | Branch/Version | Tech Status | UAT Status | PO Status | Notes / Source
PIA-DONE-001 | Foundation | Design System | PIA V3 Design System primitives | ui-v3 primitives: Card, Button, Badge, Metric, WidgetShell, Tabs, Input, EmptyState, StatusDot, MiniSparkline. | P0 | DONE | ATHENA | feat/v3-design-system-athena / 54c3595 | PASS | PASS | APPROVED | Foundation merged into integration branch.
PIA-DONE-002 | Foundation | Workspace Foundation | Workspace registry + widget catalog | Workspace metadata, widget catalog, per-workspace layout storage, AI context helper, WorkspaceSwitcher. | P0 | DONE | HERMES | feat/v3-workspace-foundation-hermes / a8f563a | PASS | PASS | APPROVED | Foundation merged into integration branch.
PIA-DONE-003 | Foundation | Workspace Activation | Live workspace navigation | Home, My Portfolio, Watchlists, Scanner, Markets & Macro, AI Infrastructure, Earnings Week, Swing Trades, Crypto, Trade Coach, Academy activated as shells. | P0 | TECH PASS | HERMES | feat/v3-workspace-activation-hermes / eac99af | PASS | UAT PENDING | PENDING | Needs visual UAT.
PIA-DONE-004 | UI/UX | Visible UI Migration | Initial V3 UI migration | Dashboard and stock intelligence migrated partly to ui-v3 primitives. | P0 | TECH PASS | ATHENA | feat/v3-ui-migration-athena / 3a103c9 | PASS | PARTIAL | NOT APPROVED | Mock compliance still far from approved mocks.
PIA-DONE-005 | Stock Intelligence | Per-stock Intelligence Panel V1 | Overview, News, Technical, Scenarios, Actions, Videos | Stock modal/sheet with tab continuity, centered modal, videos tab, chart restore, privacy and mobile fixes. | P0 | DONE | MULTI | feat/stock-intelligence-panel-v1 | PASS | PASS | APPROVED | Branch contains commits a4e1aac, 8aeb20e, 1f8597a, bb4c947, f307c60, 2458d07, 3beab33.
PIA-DONE-006 | News | News Intelligence UX V2 | Real headlines + digest + labels | Yahoo live headlines, exact URLs, PIA Digest, Bias, Confidence, Possible Move, demo gating. | P0 | DONE | MULTI | feat/news-intelligence-ux-v2 | PASS | PASS | APPROVED | Source badges evolving.
PIA-DONE-007 | Mobile | Mobile Settings Parity | Mobile settings + quick controls + bell | All settings tabs, quick controls sheet, notifications sheet. | P0 | DONE | MULTI | feat/mobile-settings-parity | PASS | PASS | APPROVED
PIA-DONE-008 | Widgets | Draggable Widgets V1 | Desktop drag/drop + mobile reorder | Widget registry, persisted layout, drag handles, mobile reorder controls. | P0 | DONE | MULTI | feat/draggable-widgets-v1 | PASS | PASS | APPROVED
PIA-BUG-024 | Bug | Market Pulse | Horizontal navigation broken | Market Pulse had no horizontal scroll/right navigation; fixed but needs UAT after integration. | P1 | TECH PASS | ATHENA/HERMES | f307c60 / integration | PASS | UAT PENDING | PENDING
PIA-BUG-026 | Bug | Hydration Warning | Browser extension fdprocessedid hydration warning | Console hydration warning caused by browser extension injecting fdprocessedid; not PIA app bug if clean browser removes it. | P2 | ENVIRONMENT | PO |  | N/A | N/A | N/A | Verify in Incognito.
PIA-BUG-027 | Bug | Dead Controls | Watch / Set alert / Risk check dead controls | Controls must be implemented or marked disabled/coming soon with honest tooltip/state. | P2 | NEW | UNASSIGNED |  |  |  |  | Trust issue.
PIA-BUG-028 | Bug | News Intelligence | Text overflow / clipping | News Intelligence cards overflow/clipping at desktop width; action columns too tight. | P1 | NEW | UNASSIGNED |  |  |  |  | Needs wrap/min-width/compact layout.
PIA-UX-029 | UX | Stock Intelligence News | Compact premium redesign | Stock news cards too spread out; need icons, compact chips, better hierarchy. | P1 | NEW | UNASSIGNED
PIA-030 | Change | Dashboard Cleanup | Remove Margin Capital Discipline from main dashboard | Removed from general dashboard; keep available later under Risk/Portfolio details. | P1 | DONE | ATHENA/HERMES | 3beab33 | PASS | PASS | APPROVED
PIA-V3-DESIGN-001 | Design System | Global Widget UX Standards | Global design system and widget standards | Locked UI rules: no raw text widgets, icons/charts/badges, hierarchy, progressive disclosure, responsive polish. | P0 | FOUNDATION DONE | ATHENA | 54c3595 | PASS | PASS | APPROVED | Further mock compliance required.
PIA-V3-001 | Workspace | Workspace Shell Redesign | PIA V3 AlphaSpace-like shell | Home + workspaces + AI Core identity + custom widgets + bottom status dock. | P0 | IN PROGRESS | ATHENA/HERMES | feat/pia-v3-foundation-integration |  | PARTIAL | PENDING | Mock compliance required.
PIA-V3-002 | Stock Workspace | Route-based stock workspace | Replace stock popup with /stock/[ticker] dedicated workspace later. | P0 | PLANNED | UNASSIGNED |  |  |  |  | Current modal remains until V3 migration.
PIA-V3-003 | AI Core | AI Core interaction layer | AI Core modes: Calm, Scanning, Risk, Alert, Coach. | P0 | PLANNED | APOLLO |  |  |  |  | Visual identity approved.
PIA-V3-004 | AI Core | Ask GPT Redirect Engine | One-click context builder redirecting to user's GPT account. | P0 | PLANNED | APOLLO |  |  |  |  | No embedded LLM initially.
PIA-V3-005 | Workspace | Saved workspaces/views | Create, clone, save layout, snapshots, import/export workspace config. | P1 | PLANNED | HERMES
PIA-V3-006 | Trade Coach | Trade Coach architecture | Live assisted trading foundation with chart, volume, VWAP, voice later. | P0 | PLANNED | APOLLO/ARTEMIS |  |  |  |  | Signature feature.
PIA-V3-007 | Heatmap | Sector / Industry Heatmap | IBKR-style sector/industry heatmap for market/portfolio/watchlist modes. | P0 | PLANNED | UNASSIGNED |  |  |  |  | Technology, Consumer, Health, etc.
PIA-V3-008 | AI Core | AI Context Builder | Collects portfolio/ticker/news/macro/discord context for GPT prompt preview. | P0 | PLANNED | APOLLO |  |  |  |  | Privacy preview required.
PIA-V3-009 | AI Core | Ask GPT Redirect Modal | Preview prompt, Copy Prompt, Open ChatGPT, Open Deep Research. | P0 | PLANNED | APOLLO
PIA-V3-010 | AI Core | Prompt Template Library | Templates: stock analysis, risk check, hedge, compare, earnings prep, Discord summary. | P1 | PLANNED | APOLLO
PIA-V3-011 | AI Core | Deep Research Redirect | Special GPT redirect for deep research mode. | P1 | PLANNED | APOLLO
PIA-V3-012 | Discord | Discord Context Summarizer | Summarize trusted Discord messages into ticker/market context. | P0 | PLANNED | APOLLO/HEPHAESTUS
PIA-V3-013 | Discord | Discord ingestion layer | Connect, choose sources, ingest trusted threads. | P0 | PLANNED | HEPHAESTUS
PIA-V3-014 | Discord | Discord ticker tagging | Detect tickers, themes, message type. | P1 | PLANNED | APOLLO
PIA-V3-015 | Discord | Discord sentiment engine | Bullish/Neutral/Bearish/Caution + confidence. | P1 | PLANNED | APOLLO
PIA-V3-016 | Discord | Discord trust scoring | Advisor vs community source trust levels. | P1 | PLANNED | APOLLO
PIA-V3-017 | Discord | Discord intelligence widgets | Market and per-stock Discord intelligence widgets. | P1 | PLANNED | ATHENA/APOLLO
PIA-V3-018 | Watchlists | Watchlists Workspace | Add/remove/sort tickers, cards/list/heatmap, logos, mini charts 1D/1W/1M. | P0 | PLANNED | HERMES/ATHENA
PIA-V3-019 | Watchlists | AI-generated watchlists | Momentum leaders, earnings risk, Discord mentions, AI conviction lists. | P1 | PLANNED | APOLLO
PIA-V3-020 | Watchlists | Watchlist heatmap | Heatmap mode for watchlist grouped by sector/industry/theme. | P1 | PLANNED | ATHENA
PIA-V3-021 | Watchlists | Watchlist alerts | Alert rules for watchlist items. | P1 | PLANNED | HEPHAESTUS/APOLLO
PIA-V3-022 | Watchlists | Discord mentions watchlist | Dynamic watchlist from Discord mentions/spikes. | P1 | PLANNED | APOLLO
PIA-V3-023 | Scanner | Scanner Workspace | Idea discovery engine with cards/table, filters, AI interpretations. | P0 | PLANNED | HERMES/ATHENA
PIA-V3-024 | Scanner | Momentum Scanner | Momentum leaders with volume/RS confirmation. | P1 | PLANNED | APOLLO
PIA-V3-025 | Scanner | Breakout Scanner | Range/ATH/reclaim/consolidation breakouts. | P1 | PLANNED | APOLLO
PIA-V3-026 | Scanner | Reversal Scanner | Oversold bounce, failed breakdown, VWAP reclaim. | P1 | PLANNED | APOLLO
PIA-V3-027 | Scanner | Earnings Scanner | Pre/post earnings opportunities and risk names. | P1 | PLANNED | APOLLO
PIA-V3-028 | Scanner | Unusual Volume Scanner | Volume >2x/3x, news-driven spikes, institutional activity candidates. | P1 | PLANNED | APOLLO
PIA-V3-029 | Scanner | AI Signals Scanner | AI high conviction/risk/trap/squeeze ideas. | P1 | PLANNED | APOLLO
PIA-V3-030 | Scanner | Saved Scans | Save custom scanner filters and alert on matches. | P1 | PLANNED | HERMES
PIA-V3-031 | Trade Coach | Trade Coach Workspace | Live assisted trading workspace with chart, plan, catalyst feed, AI coach. | P0 | PLANNED | APOLLO/ATHENA
PIA-V3-032 | Trade Coach | Live Session Engine | Ticker/session setup, position size, bias, risk, style, state machine. | P0 | PLANNED | APOLLO/HEPHAESTUS
PIA-V3-033 | Trade Coach | Trade Journal | Entry/exit/mistakes/lessons with AI comments. | P1 | PLANNED | HERMES
PIA-V3-034 | Trade Coach | Replay Mode | Review trade session after completion. | P2 | PLANNED | APOLLO
PIA-V3-035 | Trade Coach | GPT Coach Redirect | Context-rich prompt for live trade evaluation. | P0 | PLANNED | APOLLO
PIA-V3-036 | Voice | Trade Coach Voice Commands | Voice commands for trade coach: what is happening, trim, risk, etc. | P1 | PLANNED | ARTEMIS
PIA-V3-037 | Voice | Live Voice Market Updates | Calm voice updates only when material changes happen. | P1 | PLANNED | ARTEMIS
PIA-V3-038 | Voice | Calm Voice Mode | Silent/Text/Voice alerts/Full voice coach modes. | P1 | PLANNED | ARTEMIS
PIA-V3-039 | Voice | Voice Alert Thresholds | User-configured voice alert thresholds/cooldowns. | P1 | PLANNED | ARTEMIS
PIA-V3-040 | Academy | Academy Workspace | Learn mode for investing, trading, macro, crypto, psychology. | P1 | PLANNED | ATHENA/APOLLO
PIA-V3-041 | Academy | Learning Paths | Investing, Trading, Options, Macro, Crypto, Psychology, AI Infra. | P1 | PLANNED | APOLLO
PIA-V3-042 | Academy | GPT Tutor Mode | Explain simpler/deeper, quiz me, real examples. | P1 | PLANNED | APOLLO
PIA-V3-043 | Academy | Interactive Lessons | Visual explainers, scenarios, examples. | P2 | PLANNED | APOLLO/ATHENA
PIA-V3-044 | Academy | Quizzes | Simple multiple choice/scenario quizzes. | P2 | PLANNED | APOLLO
PIA-V3-045 | Academy | Trade Simulator | Practice scenarios/paper trading later. | P2 | FUTURE | APOLLO
PIA-V3-046 | Academy | Contextual Learn Buttons | Teach me this button on widgets/metrics. | P1 | PLANNED | ATHENA/APOLLO
PIA-V3-047 | Alerts | Alerts / Notifications | Alert Center | Central alert UI with categories and action cards | P1 | PLANNED | APOLLO/ARTEMIS
PIA-V3-048 | Alerts | Alerts / Notifications | Price Alerts | Above/below/crosses/% move alerts | P1 | PLANNED | APOLLO/ARTEMIS
PIA-V3-049 | Alerts | Alerts / Notifications | Macro Alerts | VIX/SKEW/DXY/10Y/liquidity/Fed alerts | P0 | PLANNED | APOLLO/ARTEMIS
PIA-V3-050 | Alerts | Alerts / Notifications | Portfolio Risk Alerts | Concentration/margin/drawdown/beta alerts | P1 | PLANNED | APOLLO/ARTEMIS
PIA-V3-051 | Alerts | Alerts / Notifications | Discord Alerts | Advisor mentions, sentiment flips, mention spikes | P1 | PLANNED | APOLLO/ARTEMIS
PIA-V3-052 | Alerts | Alerts / Notifications | AI Alerts | Thesis break, momentum fading, risk/reward deterioration | P1 | PLANNED | APOLLO/ARTEMIS
PIA-V3-053 | Alerts | Alerts / Notifications | Trade Coach Alerts | VWAP lost, volume fading, target reached | P1 | PLANNED | APOLLO/ARTEMIS
PIA-V3-054 | Alerts | Alerts / Notifications | Voice Alerts | Voice delivery for critical alerts/coach | P1 | PLANNED | APOLLO/ARTEMIS
PIA-V3-055 | Alerts | Alerts / Notifications | Natural Language Alert Builder | Create alert using plain language | P1 | PLANNED | APOLLO/ARTEMIS
PIA-V3-056 | Mobile | Mobile / Notifications | Mobile Native UX | Mobile-first native UX, not squeezed desktop | P0 | PLANNED | ARTEMIS
PIA-V3-057 | Mobile | Mobile / Notifications | Push Notification Engine | Mobile/web push notification pipeline | P0 | PLANNED | ARTEMIS
PIA-V3-058 | Mobile | Mobile / Notifications | Mobile Watchlists | Touch-first watchlist cards with gestures | P1 | PLANNED | ARTEMIS
PIA-V3-059 | Mobile | Mobile / Notifications | Mobile Trade Coach | Voice/text coach optimized for mobile | P1 | PLANNED | ARTEMIS
PIA-V3-060 | Mobile | Mobile / Notifications | Quiet Hours | Notification quiet hours and severity routing | P1 | PLANNED | ARTEMIS
PIA-V3-061 | Mobile | Mobile / Notifications | Privacy Notification Mode | Hide sensitive lock screen data | P1 | PLANNED | ARTEMIS
PIA-V3-062 | Mobile | Mobile / Notifications | Scheduled Digest | Morning/close/weekly digests | P1 | PLANNED | ARTEMIS
PIA-V3-063 | Mobile | Mobile / Notifications | Voice Mobile Alerts | Mobile spoken alerts | P1 | PLANNED | ARTEMIS
PIA-V3-064 | Integrations | Connector Architecture | Integration Hub | Settings cards with health/diagnostics for all connectors | P1 | PLANNED | HEPHAESTUS
PIA-V3-065 | Integrations | Connector Architecture | IBKR Connector | Portfolio truth source: holdings, P/L, cash, margin, orders | P0 | PLANNED | HEPHAESTUS
PIA-V3-066 | Integrations | Connector Architecture | Yahoo Connector | Quotes, fundamentals, news, company info | P0 | PLANNED | HEPHAESTUS
PIA-V3-067 | Integrations | Connector Architecture | TradingView Connector | Premium chart engine | P0 | PLANNED | HEPHAESTUS
PIA-V3-068 | Integrations | Connector Architecture | Discord Connector | Trusted threads and ticker intelligence | P1 | PLANNED | HEPHAESTUS
PIA-V3-069 | Integrations | Connector Architecture | ChatGPT Redirect Integration | Open ChatGPT with prepared context | P0 | PLANNED | HEPHAESTUS
PIA-V3-070 | Integrations | Connector Architecture | Seeking Alpha Connector | Premium research/news if access permits | P1 | PLANNED | HEPHAESTUS
PIA-V3-071 | Integrations | Connector Architecture | Macro Data Connectors | FRED, Fed, Treasury, NY Fed, CBOE | P1 | PLANNED | HEPHAESTUS
PIA-V3-072 | Integrations | Connector Architecture | Notification Connectors | Push/email/voice channels | P1 | PLANNED | HEPHAESTUS
PIA-V3-073 | Integrations | Connector Architecture | Diagnostics Panel | Connector health, latency, errors, logs | P1 | PLANNED | HEPHAESTUS
PIA-V3-074 | Settings | Personalization | Settings Architecture | Profile, Workspace, Trading, Alerts, AI, Integrations, Privacy, Mobile, Academy, System | P1 | PLANNED | HERMES/ATHENA
PIA-V3-075 | Settings | Personalization | Trading Preferences | Style, sizing, risk limits, coach tone | P1 | PLANNED | HERMES/ATHENA
PIA-V3-076 | Settings | Personalization | AI Personalities | Analyst, Coach, Tutor, Executive Brief, Hybrid | P1 | PLANNED | HERMES/ATHENA
PIA-V3-077 | Settings | Personalization | Privacy Controls | Hide amounts/P&L/holdings/title text/notification privacy | P1 | PLANNED | HERMES/ATHENA
PIA-V3-078 | Settings | Personalization | Multi Profiles | Investor/Trader/Learning profiles later | P1 | PLANNED | HERMES/ATHENA
PIA-V3-079 | Settings | Personalization | Workspace Snapshots | Manual layout snapshots and restore | P1 | PLANNED | HERMES/ATHENA
PIA-V3-080 | Settings | Personalization | Theme System | PIA Dark/Midnight/Contrast, custom colors, movie/sentiment themes later | P1 | PLANNED | HERMES/ATHENA
PIA-V3-081 | Backend | Backend / Data | Backend Architecture Refactor | Connector/normalizer/intelligence layers | P0 | PLANNED | HEPHAESTUS
PIA-V3-082 | Backend | Backend / Data | Connector Layer | Modular source connectors | P0 | PLANNED | HEPHAESTUS
PIA-V3-083 | Backend | Backend / Data | Intelligence Engine | Market/stock/portfolio/scanner/alerts engines | P1 | PLANNED | HEPHAESTUS
PIA-V3-084 | Backend | Backend / Data | AI Context Builder | Backend prompt payload builder with privacy filtering | P0 | PLANNED | HEPHAESTUS
PIA-V3-085 | Backend | Backend / Data | Notification Engine | Rules, dedup, routing, scheduled jobs | P1 | PLANNED | HEPHAESTUS
PIA-V3-086 | Backend | Backend / Data | Workspace Persistence | Persist workspace/layout/widget/user preferences | P1 | PLANNED | HEPHAESTUS
PIA-V3-087 | Backend | Backend / Data | Websocket Layer | portfolio/markets/alerts/trade-coach channels | P1 | PLANNED | HEPHAESTUS
PIA-V3-088 | Backend | Backend / Data | API Refactor | Clean /api/portfolio, /api/stocks, /api/markets etc. | P1 | PLANNED | HEPHAESTUS
PIA-V3-089 | Backend | Backend / Data | Security Layer | Encrypted creds, privacy, read-only broker enforcement | P1 | PLANNED | HEPHAESTUS
PIA-V3-090 | Portfolio | Portfolio Intelligence | Portfolio Intelligence Engine | Senior PM/risk manager intelligence for portfolio | P0 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-091 | Portfolio | Portfolio Intelligence | Exposure Heatmap | Sector/industry/theme/asset class/geography/broker exposure | P0 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-092 | Portfolio | Portfolio Intelligence | Correlation Map | Holding correlation matrix/cluster map | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-093 | Portfolio | Portfolio Intelligence | Margin Discipline | Margin, maintenance buffer, leverage risk | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-094 | Portfolio | Portfolio Intelligence | Stress Testing | Nasdaq -10%, rates spike, AI derating, BTC crash etc. | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-095 | Portfolio | Portfolio Intelligence | Hedge Builder | Puts/collars/index hedges/cash/beta reduction | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-096 | Portfolio | Portfolio Intelligence | Thesis Tracker | Why bought, bull/bear thesis, invalidation, target | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-097 | Portfolio | Portfolio Intelligence | P/L Attribution | What moved me today by ticker/sector/theme/broker | P0 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-098 | Portfolio | Portfolio Intelligence | Portfolio News Intelligence | Holdings/watchlist/theme-specific news/Discord/SA/X/Reuters | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-099 | Sources | Unified Source Badge System | Source badges in all intelligence feeds | Yahoo / Discord / SA / Reuters / PIA / X / IBKR source badges with timestamp, relevance, ticker/theme. | P0 | PLANNED | ATHENA/APOLLO
PIA-V3-100 | Sources | X/Twitter Signal Integration | Selected accounts / fast sentiment / breaking commentary. | P1 | PLANNED | HEPHAESTUS/APOLLO
PIA-V3-101 | Sources | IBKR News Connector | Detect IBKR news providers and ingest available headlines/news bulletins. | P1 | PLANNED | HEPHAESTUS
PIA-V3-102 | Markets & Macro | Macro Intelligence | Markets & Macro Workspace | Global market command center | P0 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-103 | Markets & Macro | Macro Intelligence | Sector Heatmap | Market sector heatmap | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-104 | Markets & Macro | Macro Intelligence | Macro Dashboard | VIX/SKEW/MOVE/DXY/rates/SOFR/HY | P0 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-105 | Markets & Macro | Macro Intelligence | Rates Intelligence | Yield curve, 2Y/10Y, real yields, Fed expectations | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-106 | Markets & Macro | Macro Intelligence | Volatility Intelligence | VIX/VVIX/SKEW/term structure/options stress | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-107 | Markets & Macro | Macro Intelligence | Liquidity Dashboard | TGA/RRP/SOFR/Fed balance sheet/reserves | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-108 | Markets & Macro | Macro Intelligence | Breadth Dashboard | Advance/decline, % above MA, new highs/lows | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-109 | Markets & Macro | Macro Intelligence | Macro Calendar | CPI/PPI/NFP/FOMC/GDP/speakers/auctions/OPEX | P1 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-110 | Markets & Macro | Macro Intelligence | Signals Engine | Risk-on/off, liquidity, volatility warning, rotations | P0 | PLANNED | APOLLO/ATHENA/HEPHAESTUS
PIA-V3-111 | Markets & Macro | Macro Intelligence | Custom Macro Threshold Profiles | User SKEW thresholds and alert zones | P0 | PLANNED | APOLLO/ATHENA/HEPHAESTUS |  |  |  |  | User custom SKEW framework included.
PIA-V3-112 | AI Infrastructure | AI Infra Workspace | AI Infrastructure Workspace | Sector room for AI infra names | P1 | PLANNED | ATHENA/APOLLO
PIA-V3-113 | AI Infrastructure | AI Infra Workspace | Capex Tracker | Hyperscaler capex and guidance changes | P1 | PLANNED | ATHENA/APOLLO
PIA-V3-114 | AI Infrastructure | AI Infra Workspace | Sector Leadership Board | AI infra ticker board with scores | P1 | PLANNED | ATHENA/APOLLO
PIA-V3-115 | AI Infrastructure | AI Infra Workspace | Relative Strength Comparison | Compare AI infra names visually | P1 | PLANNED | ATHENA/APOLLO
PIA-V3-116 | AI Infrastructure | AI Infra Workspace | AI Infra Intelligence Feed | Yahoo/Discord/SA/Reuters/PIA/X/IBKR feed filtered to sector | P1 | PLANNED | ATHENA/APOLLO
PIA-V3-117 | AI Infrastructure | AI Infra Workspace | Earnings War Board | AI infra earnings timeline/risk | P1 | PLANNED | ATHENA/APOLLO
PIA-V3-118 | Earnings | Earnings Tactical | Earnings Week Workspace | Event war room | P1 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-119 | Earnings | Earnings Tactical | Earnings Calendar Board | Timeline cards AMC/BMO, estimates, implied move | P1 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-120 | Earnings | Earnings Tactical | Implied Move Engine | Expected move from options | P1 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-121 | Earnings | Earnings Tactical | Surprise History | Beat/miss and post-earnings reaction history | P1 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-122 | Earnings | Earnings Tactical | Macro Collision Detection | Earnings + CPI/FOMC/macro overlap risk | P1 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-123 | Earnings | Earnings Tactical | Post Earnings Tracker | Gap/continuation/reversal/volume after results | P1 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-124 | Earnings | Earnings Tactical | Earnings AI Opportunities | Pre/post earnings ideas and traps | P1 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-125 | Earnings | Earnings Tactical | Earnings Corresponding Connector | Connector for The Earnings Corresponding account/source | P0 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-126 | Earnings | Earnings Tactical | Earnings Tactical Intelligence Engine | Prep/live interpretation/tactical decision support | P0 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-127 | Earnings | Earnings Tactical | Historical Earnings Reaction Engine | Last 5 quarters announcement/reaction analysis | P0 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-128 | Earnings | Earnings Tactical | Live Earnings Interpreter | EPS/revenue/guidance/capex delta parsing | P0 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-129 | Earnings | Earnings Tactical | Conference Call Intelligence | Tone/guidance/capex/CEO commentary | P0 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-130 | Earnings | Earnings Tactical | Earnings Tactical Trade Suggestions | Immediate event trade suggestions for holdings/watchlist | P0 | PLANNED | APOLLO/HEPHAESTUS/ATHENA |  |  |  |  | Only portfolio + watchlist companies.
PIA-V3-131 | Crypto | Crypto Workspace | Crypto Workspace | BTC/ETH/XRP/SOL/TOTAL/Dominance | P2 | PLANNED | ATHENA/APOLLO
PIA-V3-132 | Crypto | Crypto Workspace | BTC Dominance Widget | Dominance trend and rotation interpretation | P2 | PLANNED | ATHENA/APOLLO
PIA-V3-133 | Crypto | Crypto Workspace | Funding Dashboard | Funding/open interest/liquidations later | P2 | PLANNED | ATHENA/APOLLO
PIA-V3-134 | Crypto | Crypto Workspace | Crypto Macro Correlation | DXY/rates/liquidity/Nasdaq risk correlation | P2 | PLANNED | ATHENA/APOLLO
PIA-V3-135 | Crypto | Crypto Workspace | Crypto Intelligence Feed | Crypto news/Discord/X/PIA feed | P2 | PLANNED | ATHENA/APOLLO
PIA-V3-136 | Crypto | Crypto Workspace | Tactical Crypto Signals | Momentum/breakdown/reversal AI signals | P2 | PLANNED | ATHENA/APOLLO
PIA-V3-137 | Academy | Academy Core | Academy Workspace | Interactive investing/trading/macro learning workspace | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-138 | Academy | Academy Core | Learning Paths | Investing/trading/options/macro/crypto/psychology/AI infra | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-139 | Academy | Academy Core | AI Tutor | GPT tutor modes | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-140 | Academy | Academy Core | Interactive Lessons | Visual lessons and examples | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-141 | Academy | Academy Core | Quiz Engine | Quiz and scenario checks | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-142 | Academy | Academy Core | Contextual Learning Buttons | Teach me this from any widget | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-143 | Academy | Academy Core | Progress Tracking | Completed lessons, weak areas, recommendations | P2 | PLANNED | APOLLO/ATHENA
PIA-V3-144 | Academy | Academy Core | Scenario Practice | Market/trade scenario drills | P2 | PLANNED | APOLLO/ATHENA
PIA-V3-145 | Academy | Great Investors / Resilience | Great Investors Learning Path | Buffett, Ackman, Druckenmiller, Howard Marks, Dalio, Lynch, Soros | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-146 | Academy | Great Investors / Resilience | Portfolio Construction Academy | Build resilient portfolio, allocation, sizing, diversification | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-147 | Academy | Great Investors / Resilience | Resilient Portfolio Training | Surviving drawdowns, capital preservation, crash psychology | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-148 | Academy | Great Investors / Resilience | Hedging Education | Puts, collars, index hedges, cash, sector hedges | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-149 | Academy | Great Investors / Resilience | Margin Discipline Training | Good leverage, bad leverage, maintenance risk | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-150 | Academy | Great Investors / Resilience | Investor Simulation Modules | Build Buffett/Druckenmiller portfolios, stress test current portfolio | P1 | PLANNED | APOLLO/ATHENA
PIA-V3-151 | Workspace | Custom Workspace Engine | Custom Workspace Builder | Create custom workspace wizard | P1 | PLANNED | HERMES/ATHENA/APOLLO
PIA-V3-152 | Workspace | Custom Workspace Engine | Widget Library | Add Widget library with categories/search | P1 | PLANNED | HERMES/ATHENA/APOLLO
PIA-V3-153 | Workspace | Custom Workspace Engine | AI Workspace Generator | Natural language workspace creation | P1 | PLANNED | HERMES/ATHENA/APOLLO
PIA-V3-154 | Workspace | Custom Workspace Engine | Workspace Templates | Portfolio, Macro, Trading, Earnings, Academy templates | P1 | PLANNED | HERMES/ATHENA/APOLLO
PIA-V3-155 | Workspace | Custom Workspace Engine | Workspace Snapshots | Save/restore layout snapshots | P1 | PLANNED | HERMES/ATHENA/APOLLO
PIA-V3-156 | Workspace | Custom Workspace Engine | Separate Mobile Layouts | Different desktop/mobile workspace layouts | P1 | PLANNED | HERMES/ATHENA/APOLLO
PIA-V3-157 | Workspace | Custom Workspace Engine | Workspace AI Context Profiles | Workspace-specific AI focus and prompts | P1 | PLANNED | HERMES/ATHENA/APOLLO
PIA-V3-158 | Command | Omnibox / Command Palette | Global Omnibox | Ask PIA/search ticker/create alert/compare | P1 | PLANNED | HERMES/APOLLO/ATHENA
PIA-V3-159 | Command | Omnibox / Command Palette | Command Palette | Ctrl+K command center | P1 | PLANNED | HERMES/APOLLO/ATHENA
PIA-V3-160 | Command | Omnibox / Command Palette | AI Intent Router | Detect ticker/workspace/widget/GPT/alert/academy/coach intent | P1 | PLANNED | HERMES/APOLLO/ATHENA
PIA-V3-161 | Command | Omnibox / Command Palette | Natural Language Commands | Create alert, compare, open coach, teach me | P1 | PLANNED | HERMES/APOLLO/ATHENA
PIA-V3-162 | Command | Omnibox / Command Palette | Widget Quick Add | Add widgets from command palette | P1 | PLANNED | HERMES/APOLLO/ATHENA
PIA-V3-163 | Command | Omnibox / Command Palette | Workspace Quick Navigation | Quick jump across workspaces | P1 | PLANNED | HERMES/APOLLO/ATHENA
PIA-V3-164 | Command | Omnibox / Command Palette | Context Aware Suggestions | Suggestions depend on current workspace/ticker | P1 | PLANNED | HERMES/APOLLO/ATHENA
PIA-V3-165 | Notes | Notes / Thesis / Journal | Notes System | Text notes tied to ticker/portfolio/workspace | P1 | PLANNED | HERMES/APOLLO/ARTEMIS
PIA-V3-166 | Notes | Notes / Thesis / Journal | Voice Notes | Dictated notes with transcription and AI summary | P1 | PLANNED | HERMES/APOLLO/ARTEMIS
PIA-V3-167 | Notes | Notes / Thesis / Journal | Thesis Tracker | Structured thesis fields per holding | P1 | PLANNED | HERMES/APOLLO/ARTEMIS
PIA-V3-168 | Notes | Notes / Thesis / Journal | AI Thesis Monitoring | Check if thesis intact based on news/macro/data | P1 | PLANNED | HERMES/APOLLO/ARTEMIS
PIA-V3-169 | Notes | Notes / Thesis / Journal | Trade Journal | Trade entries/exits/mistakes/lessons | P1 | PLANNED | HERMES/APOLLO/ARTEMIS
PIA-V3-170 | Notes | Notes / Thesis / Journal | Voice Trade Journal | Voice post-trade journal | P1 | PLANNED | HERMES/APOLLO/ARTEMIS
PIA-V3-171 | Notes | Notes / Thesis / Journal | Research Vault | Saved articles/GPT analyses/screenshots/videos/Discord insights | P1 | PLANNED | HERMES/APOLLO/ARTEMIS
PIA-V3-172 | Notes | Notes / Thesis / Journal | Idea Inbox | Fast capture ideas, text/voice | P1 | PLANNED | HERMES/APOLLO/ARTEMIS
PIA-V3-173 | Notes | Notes / Thesis / Journal | Notes Search | Global search across notes/voice/transcripts | P1 | PLANNED | HERMES/APOLLO/ARTEMIS
PIA-V3-174 | Portfolio | History / Snapshots | Portfolio History Engine | History and analytics engine | P0 | PLANNED | HEPHAESTUS/APOLLO/ATHENA |  |  |  |  | Storage efficient required.
PIA-V3-175 | Portfolio | History / Snapshots | Daily Snapshot Storage | Daily portfolio snapshots for 2 years | P0 | PLANNED | HEPHAESTUS/APOLLO/ATHENA |  |  |  |  | Storage efficient required.
PIA-V3-176 | Portfolio | History / Snapshots | Per-stock Snapshots | Daily ticker snapshots for holdings/watchlist | P1 | PLANNED | HEPHAESTUS/APOLLO/ATHENA |  |  |  |  | Storage efficient required.
PIA-V3-177 | Portfolio | History / Snapshots | P/L Attribution | What moved portfolio today | P0 | PLANNED | HEPHAESTUS/APOLLO/ATHENA |  |  |  |  | Storage efficient required.
PIA-V3-178 | Portfolio | History / Snapshots | IBKR-style Performance Chart | 1D/1W/1M/3M/YTD/1Y/2Y/All with benchmarks | P0 | PLANNED | HEPHAESTUS/APOLLO/ATHENA |  |  |  |  | Storage efficient required.
PIA-V3-179 | Portfolio | History / Snapshots | Event Timeline Overlay | Trades/earnings/macro/news/alerts/notes overlay | P1 | PLANNED | HEPHAESTUS/APOLLO/ATHENA |  |  |  |  | Storage efficient required.
PIA-V3-180 | Portfolio | History / Snapshots | Drawdown Analytics | Largest drawdown, duration, drivers, macro context | P1 | PLANNED | HEPHAESTUS/APOLLO/ATHENA |  |  |  |  | Storage efficient required.
PIA-V3-181 | Portfolio | History / Snapshots | Snapshot Compare | Compare two dates allocation/risk/performance | P1 | PLANNED | HEPHAESTUS/APOLLO/ATHENA |  |  |  |  | Storage efficient required.
PIA-V3-182 | Portfolio | History / Snapshots | Daily AI Portfolio Recap | Daily explanation of drivers and context | P1 | PLANNED | HEPHAESTUS/APOLLO/ATHENA |  |  |  |  | Storage efficient required.
PIA-V3-183 | Performance | Performance & Storage | Performance Budget System | Resource budgets for widgets/connectors | P0 | PLANNED | HEPHAESTUS/HERMES
PIA-V3-184 | Performance | Performance & Storage | Storage Retention Policy | Daily 2y, intraday short-term, cleanup jobs | P0 | PLANNED | HEPHAESTUS/HERMES
PIA-V3-185 | Performance | Performance & Storage | Snapshot Compression Strategy | Compressed/summarized historical snapshots | P1 | PLANNED | HEPHAESTUS/HERMES
PIA-V3-186 | Performance | Performance & Storage | Lazy Widget Loading | Render/fetch widgets only when visible/active | P0 | PLANNED | HEPHAESTUS/HERMES
PIA-V3-187 | Performance | Performance & Storage | Mobile Performance Mode | Reduced polling/animations/live updates on mobile | P0 | PLANNED | HEPHAESTUS/HERMES
PIA-V3-188 | Performance | Performance & Storage | Connector Caching Layer | Batch/cache/rate-limit provider calls | P1 | PLANNED | HEPHAESTUS/HERMES
PIA-V3-189 | Performance | Performance & Storage | Resource Monitor | Storage/CPU/network diagnostics | P1 | PLANNED | HEPHAESTUS/HERMES
PIA-V3-190 | Backup | Cloud Backup / Restore | Cloud Backup System | Backup settings/layouts/watchlists/alerts/notes/progress | P1 | PLANNED | HEPHAESTUS/HERMES |  |  |  |  | User chooses own cloud.
PIA-V3-191 | Backup | Cloud Backup / Restore | Encrypted Export / Import | Manual encrypted export/import file | P1 | PLANNED | HEPHAESTUS/HERMES |  |  |  |  | User chooses own cloud.
PIA-V3-192 | Backup | Cloud Backup / Restore | Google Drive Backup | User-owned cloud backup | P1 | PLANNED | HEPHAESTUS/HERMES |  |  |  |  | User chooses own cloud.
PIA-V3-193 | Backup | Cloud Backup / Restore | OneDrive Backup | User-owned cloud backup | P1 | PLANNED | HEPHAESTUS/HERMES |  |  |  |  | User chooses own cloud.
PIA-V3-194 | Backup | Cloud Backup / Restore | Restore Wizard | New device restore flow | P1 | PLANNED | HEPHAESTUS/HERMES |  |  |  |  | User chooses own cloud.
PIA-V3-195 | Backup | Cloud Backup / Restore | Backup Retention Versions | Versioned restore points | P1 | PLANNED | HEPHAESTUS/HERMES |  |  |  |  | User chooses own cloud.
PIA-V3-196 | Backup | Cloud Backup / Restore | Secure Credential Re-auth Flow | Do not store broker/secrets in plain backup | P1 | PLANNED | HEPHAESTUS/HERMES |  |  |  |  | User chooses own cloud.
PIA-V3-197 | Stock Workspace | Analyst Targets Intelligence Widget | Per-stock targets: avg/bull/bear target, upside/downside %, analyst count, revisions, trend changes. | P0 | PLANNED | ATHENA/HEPHAESTUS/APOLLO |  |  |  |  | Required per stock; source badge aware.
PIA-V3-198 | DevOps | Vercel Preview Deploy | Branch preview deployment for mobile UAT from phone. | P0 | PLANNED | HEPHAESTUS |  |  |  |  | Recommended before BlueOcean.
PIA-V3-199 | DevOps | BlueOcean / DigitalOcean staging | Later staging server for backend + frontend + jobs. | P1 | LATER | HEPHAESTUS
PIA-V3-200 | Process | Backlog XLSX + Git Source of Truth | Keep master backlog in XLSX and git markdown/JSON file, updated every delivery. | P0 | IN PROGRESS | PROJECT_MANAGER |  |  |  |  | This file.
ID | Priority | Area | Item | Owner | Severity | Sprint | Status | Notes
PIA-BL-001 | P0 | News UX V2 | Real article titles | TBD | MEDIUM | TBD | Planned | Use backend-provided real titles
PIA-BL-002 | P0 | News UX V2 | Exact article links | TBD | MEDIUM | TBD | Planned | Preserve source URLs
PIA-BL-003 | P0 | News UX V2 | PIA Digest section | TBD | MEDIUM | TBD | Planned | Decision-relevance summary
PIA-BL-004 | P0 | News UX V2 | Bias instead of Sentiment | TBD | LOW | TBD | Planned | Decision-friendly language
PIA-BL-005 | P0 | News UX V2 | Confidence instead of Impact | TBD | LOW | TBD | Planned | Confidence framing
PIA-BL-006 | P0 | Routing | Release Center opens Academy incorrectly | HERMES | HIGH | DONE | HERMES fixed 2026-05-28 | Release Center routing mismatch
PIA-BL-007 | P0 | Mobile Home | Market Pulse swipe gestures failing | ATHENA | HIGH | 2C | Planned | Swipe gestures failing
PIA-BL-008 | P0 | Home Dashboard | Home widgets not clickable | ATHENA | CRITICAL | 2C | Planned | Likely pointer-events/z-index issue
PIA-BL-009 | P0 | Performance | Mobile stutter and smoothness degradation | ATHENA + HERMES | HIGH | 2C | Planned | Motion/render cost issue
PIA-BL-010 | P0 | Notifications | Notification Center responsive failure | ARTEMIS | CRITICAL | 2C | Planned | Broken wrapping and mobile invisible state
PIA-BL-011 | P1 | Technical Snapshot | Expansion | ATHENA + HERMES | MEDIUM | 2C | Planned | Support/resistance, AI interpretation, trade scenarios, confidence meter, multi-timeframe modes
PIA-BL-012 | P1 | Company Research | Hub refactor | HERMES | MEDIUM | 2C | Planned | Merge Earnings, Financials, Ratios, Targets inside Company tab
PIA-BL-013 | P1 | Videos | Experience rework | HERMES | MEDIUM | 2C | Planned | YouTube-style previews, featured media, thumbnail hierarchy
PIA-BL-014 | P1 | Scanner | Opportunity Board compression | ATHENA | MEDIUM | 2C | Planned | Compact filter chips, remove oversized sort controls, mobile-first scanner rail
PIA-BL-015 | P0 | Notifications | Notification Center refactor | ARTEMIS | CRITICAL | 2C | Planned | Mobile-safe sheet, grouped notifications, premium stacked cards, category identities
PIA-BL-016 | P1 | Intelligence Cards | Density refactor | ATHENA + HERMES | MEDIUM | 2C | Planned | Reduce oversized horizontal cards; compact mobile cards; expandable density system
S2C-MOBILE-STABILIZATION | Mobile/Home | Sprint 2C stabilization | Mobile-critical interaction fixes | Fixed Home click targets, Market Pulse swipe, mobile notification sheet/cards, compact scanner sort controls, and first-pass mobile render cost. | P0 | DONE | ATHENA + ARTEMIS | Sprint 2C | 2026-05-28 | 2026-05-28 | v0.3.1 | Build and route validation passed; Release Center routing remains with HERMES.
S2C-STOCK-INTEL-REFINEMENT | Stock Intelligence | Sprint 2C stock workspace refinement | Technical decision workflow, Company hub, media-first Videos, compact News cards, Release Center routing fix. | P1 | DONE | HERMES | 2026-05-28
DESIGN-GOV-MOCK-FIRST | Platform | Design Governance | Mock-first design governance system | Created locked design-system docs and mock storage hierarchy. UI implementation now requires approved mock, design-system rule, mobile-first principle, and changelog reference. | P0 | DONE | ATHENA + HERMES | Sprint 2C | 2026-05-28 | 2026-05-28 | v0.3.5 | Portfolio Snapshot redesign is blocked until approved mobile mock.
DESIGN-GOV-MOCK-FIRST | Platform | Design Governance | Mock-first design governance system | Created locked design-system docs and mock storage hierarchy. UI implementation now requires approved mock, design-system rule, mobile-first principle, and changelog reference. | P0 | DONE | ATHENA + HERMES | Sprint 2C | 2026-05-28 | 2026-05-28 | v0.3.5 | Portfolio Snapshot redesign is blocked until approved mobile mock.
DATA-HYBRID-MOCK-LAYER | Platform | Data Layer | Hybrid mock intelligence data layer | Created backend/mock_intelligence_data.py with Bloomberg-lite mock data for NVDA, AMD, SOFI, IREN, AVAV, GOOGL, TSLA, CRWV, NBIS. Includes company profile, financials, ratios, earnings, analyst targets, and technical levels. Integrated into /stock/{ticker} intelligence response. IREN added to positions; AVAV+TSLA added to watchlist. Live news/videos preserved. | P0 | DONE | HEPHAESTUS + APOLLO | Sprint 2C | 2026-05-28 | 2026-05-28 | v0.3.6 | Mock prices calibrated to 2026-05-28. Live IBKR or Yahoo needed for real-time prices.

## Roadmap
Phase | Theme | Objective | Key Deliverables | Primary Owner | Status | UAT Gate
Sprint 1 | Foundation | Establish V3 platform foundations | ui-v3 primitives; workspace registry; widget catalog; docs | ATHENA/HERMES | DONE | PASS
Sprint 2 | Activation + Initial Visuals | Activate workspace nav and initial UI migration | Workspace switching; placeholders; V3 primitives applied to dashboard/stock | ATHENA/HERMES | TECH PASS | UAT PARTIAL
Sprint 2B | Mock Compliance | Bring visible UI closer to approved mocks | Mobile Home; stock/news/videos; source badges; targets placeholder; status dock | ATHENA/HERMES | READY | MOCK COMPLIANCE REQUIRED
Sprint 3 | Portfolio V3 MVP | Make My Portfolio the first real V3 workspace | Snapshot, holdings, heatmap, attribution, performance chart, risk summary | ATHENA/HERMES/HEPHAESTUS/APOLLO | PLANNED | Mobile-first + desktop
Sprint 4 | Stock Workspace V3 | Move from modal toward dedicated stock workspace | Chart, News, Videos, Targets, Discord, Notes, Trade Coach placeholder | ATHENA/HERMES/HEPHAESTUS | PLANNED | Mock parity
Sprint 5 | Backend Backbone | Stabilize connectors/data contracts | IBKR/Yahoo normalization, cache, health state, API contracts | HEPHAESTUS | PLANNED | Endpoint + degraded state
Sprint 6 | Intelligence Layer | Make PIA think | Scoring, AI context builder, GPT redirect, alerts, macro signals | APOLLO | PLANNED | Explainability + no fake data
Later | Mobile Preview / Staging | Enable UAT from phone | Vercel preview, later BlueOcean staging | HEPHAESTUS | PLANNED | Branch URL available
Phase | Theme | Scope | Exit Criteria
Sprint 2B | UX direction and mock compliance | Stock workspace improvements, mobile/home refinements, governance updates | Implementation branches merged and governance updated
Sprint 2C | UAT failure remediation and density pass | Routing mismatch, swipe gestures, widget clickability, performance, Notification Center responsiveness | Critical UAT failures fixed and mobile interactions stable
V3 Foundation | Workspace platform | Configurable workspaces with existing widgets | Workspace registry and widget catalog remain source of truth
V3 Intelligence | Stock intelligence expansion | Analyst targets, unified feed, per-stock targets | Each stock detail has actionable intelligence
V3 Portfolio Ops | Watchlists and scanner depth | Watchlist operations, scanner workflows, heatmaps | Workspaces feel operational
Sprint 2C | Stock workspace intelligence refinement | Make stock workspace mobile-first and decision-oriented. | Technical decision workflow; Company fundamentals hub; media-first Videos; compact News; Release Center routing fix. | HERMES | DONE | Build/routes PASS
Sprint 2C | Design Governance | Lock mock-first workflow before further UI implementation | Design-system docs; mock folders; mandatory PO review gate; Portfolio Snapshot mobile mock gate | ATHENA + HERMES | DONE | Mock-first gate required before UI changes
Sprint 2C | Design Governance | Lock mock-first workflow before further UI implementation | Design-system docs; mock folders; mandatory PO review gate; Portfolio Snapshot mobile mock gate | ATHENA + HERMES | DONE | Mock-first gate required before UI changes
Sprint 2C | Data Layer | Deploy hybrid mock intelligence data for UI evaluation | backend/mock_intelligence_data.py; state.py IREN+AVAV+TSLA; stock_intelligence.py merge | HEPHAESTUS + APOLLO | DONE | Live news/videos preserved; mock used for fundamentals and technicals only

## Architecture Decisions
Decision ID | Area | Decision | Status | Rationale / Notes
DEC-001 | Product | Mobile-first: 90% mobile, 10% desktop | LOCKED | Desktop is power workspace; mobile is primary product.
DEC-002 | Architecture | Local-first architecture | LOCKED | Privacy, speed, lower cost; cloud backup optional.
DEC-003 | Auth | Simple login later | LOCKED | Needed for backup/sync and multi-device restore.
DEC-004 | Charts | TradingView chart engine | LOCKED | Best practical chart UX.
DEC-005 | AI | AI Redirect Mode to user's GPT account | LOCKED | Context builder + preview + one-click ChatGPT; no embedded LLM initially.
DEC-006 | Privacy | Privacy mode mandatory | LOCKED | Hide amounts/P&L/visible investor titles when public.
DEC-007 | Widgets | Everything is a widget | LOCKED | Custom workspaces with resizable panels.
DEC-008 | Status | IBKR/Yahoo/Feeds/GPT status dock bottom-left | LOCKED | Avoid top-right clutter.
DEC-009 | Workspaces | Home + My Portfolio + Watchlists + Scanner + Markets & Macro + AI Infra + Earnings Week + Swing Trades + Crypto + Trade Coach + Academy | LOCKED | First-class workspace architecture.
DEC-010 | Sources | Unified source badges: Yahoo, Discord, SA, Reuters, PIA, X, IBKR | LOCKED | Every intelligence item should show source/time/relevance.
DEC-011 | Stock | Analyst targets required per stock | LOCKED | Targets widget with avg/bull/bear/upside/revisions.
DEC-012 | Storage | Efficient snapshots: daily 2y, intraday short-term | LOCKED | Storage/resource efficiency required.
DEC-013 | Backup | User-owned encrypted cloud backup/import | LOCKED | Google Drive/OneDrive/manual encrypted export; re-auth secrets.
DEC-014 | Design | Approved mocks are source of truth | LOCKED | No surprise redesigns; mock compliance required.
ID | Decision | Rationale | Status
ADR-001 | Preserve existing architecture | Avoid route and feature regressions | Approved
ADR-002 | Everything is a widget | Supports configurable workspace platform | Approved
ADR-003 | Reuse current dashboard widgets | Prevent duplicate widgets/pages | Approved
ADR-004 | Mobile customization uses workspace/widget registry | Keeps mobile and desktop aligned | Approved
ADR-005 | Local layout storage is local-first and keyed by workspace ID | Fast and resilient customization | Approved
ADR-006 | Final stock tab order: Quote, Technical, News, Company, Videos | Locks navigation model for Sprint 2C | Approved
ADR-007 | Company tab absorbs Earnings, Financials, Ratios, and Targets | Reduces tab sprawl while preserving research depth | Approved
ADR-008 | Technical tab owns support/resistance, AI interpretation, scenarios, confidence, and timeframe modes | Keeps actionable trading context in one workspace | Approved
ADR-009 | Videos tab requires media-first previews and thumbnail hierarchy | Prevents video intelligence from reading as raw text lists | Approved
ADR-010 | Notification Center must be mobile-safe grouped premium cards | Fixes responsive failure and establishes category identity | Approved
ADR-011 | Routing | Release Center uses explicit #tool=about routing so persisted workspace state cannot reopen Academy. | Approved | Fixes Sprint 2C Release Center routing mismatch without changing workspace registry architecture.
DEC-MOCK-FIRST | Design Governance | Mock-first development is mandatory before UI implementation | LOCKED | No widget, screen, workspace, navigation change, or major refactor may be implemented before mock creation, PO review, corrections, APPROVED status, and storage in docs/design-system/mocks/.
DEC-MOCK-FIRST | Design Governance | Mock-first development is mandatory before UI implementation | LOCKED | No widget, screen, workspace, navigation change, or major refactor may be implemented before mock creation, PO review, corrections, APPROVED status, and storage in docs/design-system/mocks/.

## UAT Log
UAT ID | Date | Area | Scenario | Expected | Result | PO Status | Notes
UAT-001 | 2026-05-26 | Sprint 1 Foundation | Dashboard/mobile/setup still load after foundation merge | No regressions | PASS | APPROVED | Functional only; no visible redesign expected.
UAT-002 | 2026-05-26 | Stock Intelligence | Centered modal, chart restore, mobile sheet focus, privacy masking, manual holdings overflow | All fixed | PASS | APPROVED | Previously approved.
UAT-003 | 2026-05-26 | Market Pulse | Horizontal navigation/scroll works desktop and mobile | Can move between indicators | TECH PASS | PENDING | Needs user UAT after integration.
UAT-004 | 2026-05-26 | V3 Workspace Activation | Workspace switcher, placeholders, persistence, hash routing | Home + workspaces available and stable | TECH PASS | PENDING | Needs visual/functional UAT.
UAT-005 | 2026-05-26 | V3 UI Migration | Dashboard and stock view visually closer to approved mocks | Significant visual transformation | PARTIAL/FAIL | NOT APPROVED | User said not enough visible change; mock compliance required.
UAT-006 | TBD | Sprint 2B Home | Mobile-first Home mock compliance | Premium mobile-first executive dashboard | PENDING | PENDING | Athena task ready.
UAT-007 | TBD | Sprint 2B Stock | Stock/news/videos/technical mock compliance | Premium stock workspace quality, compact news/videos, targets placeholder | PENDING | PENDING | Hermes task ready.
ID | Scenario | Expected Result | Owner | Severity | Sprint | Status
UAT-001 | Build frontend | npm run build passes | ATHENA | HIGH | 2B | Required before commit
UAT-002 | Load / | Home route returns 200 | ATHENA | HIGH | 2B | Required before commit
UAT-003 | Load /mobile | Mobile route returns 200 | ATHENA | HIGH | 2B | Required before commit
UAT-004 | Load /setup | Setup route returns 200 | ATHENA | HIGH | 2B | Required before commit
UAT-005 | Privacy toggle | Amount visibility toggles and persists | ATHENA | HIGH | 2B | Required before commit
UAT-006 | Mobile overflow | Mobile loads without horizontal overflow | ATHENA | HIGH | 2B | Required before commit
UAT-011 | Release Center routing mismatch | Release Center must not open Academy incorrectly | HERMES | HIGH | PASS | APPROVED | Fixed 2026-05-28 via explicit #tool=about routing; route smoke checks pass.
UAT-012 | Market Pulse swipe | Swipe gestures must work on mobile Market Pulse | ATHENA | HIGH | 2C | Failed
UAT-013 | Home widget clickability | Home widgets must be clickable and not blocked by pointer-events/z-index | ATHENA | CRITICAL | 2C | Failed
UAT-014 | Mobile performance smoothness | Mobile interactions must not stutter from excessive motion/render cost | ATHENA + HERMES | HIGH | 2C | Failed
UAT-015 | Notification Center responsiveness | Notification Center must wrap correctly and remain visible on mobile | ARTEMIS | CRITICAL | 2C | Failed
UAT-S2C-MOBILE | 2026-05-28 | Mobile/Home | Validate mobile interactions and routes | Home widgets clickable; Market Pulse swipes; bell opens mobile-safe notification sheet; scanner controls compact; privacy mode preserved; routes return 200. | PASS | APPROVED | npm run build passed; /, /mobile, and /setup returned 200. Real-device performance profiling remains recommended.
UAT-S2C-STOCK | 2026-05-28 | Stock Workspace | Validate locked tab order, Technical decision workflow, Company hub, Videos last, compact News cards, Release Center routing, and routes. | Build passes; /, /mobile, /setup return 200; Release Center opens about tool route. | PASS | APPROVED | npm run build passed. Interactive browser console not available; route smoke checks passed.

## Approved Mocks
Mock ID | Screen / Component | Design Intent | Status | Acceptance Notes
MOCK-001 | PIA Design System | Dark institutional UI, glass/neon, premium cards, typography, badges, metrics | APPROVED | Use as strict visual direction; no surprise redesigns.
MOCK-002 | Portfolio / Stock Cards | Stock cards and portfolio cards with logos, metrics, mini charts, badges, polished density | APPROVED | Cards must include icons/logos, badges, and trend visuals.
MOCK-003 | Stock Workspace | Per-stock page/workspace with chart, news, videos, tabs, AI insights, actions | APPROVED | Current modal far from final; Sprint 2B and later dedicated /stock route required.
MOCK-004 | Mobile PIA | Mobile-first screens with compact cards, bottom/user-friendly nav, premium dark style | APPROVED | Mobile is primary acceptance target.
MOCK-005 | AI Core Identity | Orb/AI core state machine: Calm, Scanning, Risk, Alert, Coach | APPROVED | Signature identity; can be widget/rail, not mandatory fixed column.
MOCK-006 | AlphaSpace-like Workspace | Custom modular workspace, everything widget, resizable, saved views | APPROVED | Ticker strip not fixed; should be optional widget.
Area | Approved Direction
Visual identity | Premium dark, glass, neon accents, cinematic depth
Dashboard density | Compact, information-rich, readable cards
Mobile Home | Polished one-hand command experience, not squeezed desktop
Workspace selector | Obvious active workspace and intentional navigation
Status | Bottom-left dock or compact mobile status surface
Stock tab order | Quote, Technical, News, Company, Videos
Technical Snapshot | Support/resistance, AI interpretation, trade scenarios, confidence meter, multi-timeframe modes
Company Research | Merge Earnings, Financials, Ratios, Targets inside Company tab
Videos | YouTube-style previews, featured media, thumbnail hierarchy
Opportunity Board | Compact filter chips, remove oversized sort controls, mobile-first scanner rail
Notification Center | Mobile-safe sheet, grouped notifications, premium stacked cards, category identities
Intelligence Cards | Reduce oversized horizontal cards, compact mobile cards, expandable density system
MOCK-GOV-001 | Mock-first governance | Approved mocks are mandatory implementation references and must live under docs/design-system/mocks/. | LOCKED | Portfolio Snapshot requires approved mobile mock before redesign.
MOCK-GOV-001 | Mock-first governance | Approved mocks are mandatory implementation references and must live under docs/design-system/mocks/. | LOCKED | Portfolio Snapshot requires approved mobile mock before redesign.

## Agent Tasks
Task ID | Agent | Branch | Mission | Scope | Commit / Status | Validation | Next Action
TASK-ATHENA-S1 | ATHENA | feat/v3-design-system-athena | Design system primitives | ui-v3 primitives and tokens | 54c3595 DONE | Build/routes PASS | Integrated
TASK-HERMES-S1 | HERMES | feat/v3-workspace-foundation-hermes | Workspace foundation | Registry, catalog, layout storage, context, docs | a8f563a DONE | Build/routes PASS | Integrated
TASK-HERMES-S2 | HERMES | feat/v3-workspace-activation-hermes | Workspace activation | Live switcher, persistence, placeholders | eac99af TECH PASS | Build/routes PASS | UAT pending
TASK-ATHENA-S2 | ATHENA | feat/v3-ui-migration-athena | Visible UI migration | Dashboard/stock migrated partially to ui-v3 | 3a103c9 TECH PASS | Build/routes PASS | Mock compliance failed/partial
TASK-ATHENA-S2B | ATHENA | feat/v3-mobile-home-mock-athena | Mobile-first Home mock compliance | Home/mobile shell, widget density, status dock, workspace selector | READY | Must build + route smoke | Run next
TASK-HERMES-S2B | HERMES | feat/v3-stock-mock-compliance-hermes | Stock mock compliance | Stock modal/sheet, news/videos, targets placeholder, actions honest state | READY | Must build + route smoke | Run next
TASK-HEPHAESTUS-S3 | HEPHAESTUS | TBD | Backend stabilization | Connector architecture, IBKR/Yahoo normalization, health/cache | PLANNED | Endpoint + degraded mode tests | After Sprint 2B
Agent | Task | Branch | Commit Requirement | Status
ATHENA | Sprint 2B mobile-first Home mock compliance | feat/v3-mobile-home-mock-athena | feat: improve mobile-first home mock compliance | Merged
HERMES | Stock intelligence mock compliance | feat/v3-stock-mock-compliance-hermes | feat: improve stock intelligence mock compliance | Merged
ATHENA + HERMES | Finalize Sprint 2B UX direction and governance updates | feat/pia-v3-foundation-integration | feat: finalize sprint 2B UX direction and governance updates | In progress
HERMES | Fix Release Center routing mismatch | feat/pia-v3-foundation-integration | TBD | Planned Sprint 2C
ATHENA | Fix Market Pulse swipe gestures | feat/pia-v3-foundation-integration | TBD | Planned Sprint 2C
ATHENA | Fix Home widget clickability | feat/pia-v3-foundation-integration | TBD | Planned Sprint 2C
ATHENA + HERMES | Reduce mobile performance lag | feat/pia-v3-foundation-integration | TBD | Planned Sprint 2C
ARTEMIS | Refactor Notification Center responsiveness | feat/pia-v3-foundation-integration | TBD | Planned Sprint 2C
TASK-S2C-MOBILE-STABILIZATION | ATHENA + ARTEMIS | feat/pia-v3-foundation-integration | Mobile-first stabilization | Home interactions, Market Pulse swipe, Notification Center bottom sheet, stacked notification cards, compact scanner controls, and performance smoothing. | IMPLEMENTED | Build passed; routes 200 | HERMES keeps Release Center routing mismatch; profile mobile performance on device.
TASK-S2C-STOCK-INTEL-REFINEMENT | HERMES | feat/pia-v3-foundation-integration | Stock workspace intelligence refinement | Quote/Technical/News/Company/Videos tabs, trade-entry Technical workflow, About/Fundamentals Company hub, media-first Videos, compact News, Release Center routing. | IMPLEMENTED | Build passed; routes 200 | Live fundamentals/targets provider integration remains future work.
TASK-DESIGN-GOV-MOCK-FIRST | ATHENA + HERMES | feat/pia-v3-foundation-integration | Design governance + mock-first workflow | Create design-system docs, mock directories, mandatory mock-first rules, Portfolio Snapshot gate, and governance updates. | IMPLEMENTED | Docs diff/check clean | Use approved mocks before further UI implementation.
TASK-DESIGN-GOV-MOCK-FIRST | ATHENA + HERMES | feat/pia-v3-foundation-integration | Design governance + mock-first workflow | Create design-system docs, mock directories, mandatory mock-first rules, Portfolio Snapshot gate, and governance updates. | IMPLEMENTED | Docs diff/check clean | Use approved mocks before further UI implementation.

## CURRENT_STATE
CURRENT ACTIVE STATE
Active Branch | feat/pia-v3-foundation-integration
Stable Checkpoint | 758dad7d1e0b8781b38fd9737e4e3a4a8afaf625
Current Sprint | Sprint 2C
OPEN CRITICAL BUGS
Release Center routing mismatch | FIXED 2026-05-28
Market Pulse swipe broken | OPEN
Home widgets not clickable | OPEN
Notification Center responsive failure | OPEN
Performance lag / smoothness degradation | OPEN
LOCKED UX DECISIONS
Stock tab order | Quote / Technical / News / Company / Videos
Technical Direction | IBKR-inspired decision workspace
Company Tab | Fundamentals research hub
Videos | YouTube-style research discovery
Architecture | Mobile-first investment operating system
Sprint 2C mobile stabilization | DONE 2026-05-28: Home clickability, Market Pulse swipe, mobile Notification Center, compact scanner controls, and first-pass performance smoothing.
Sprint 2C stock workspace refinement | DONE 2026-05-28: locked tabs, Technical decision workflow, Company hub, Videos last, compact News, Release Center routing fix.
Design Governance | LOCKED 2026-05-28: Mock-first development is mandatory; approved mocks must be stored under docs/design-system/mocks/ before UI implementation.
Design Governance | LOCKED 2026-05-28: Mock-first development is mandatory; approved mocks must be stored under docs/design-system/mocks/ before UI implementation.
Data Layer | DONE 2026-05-28: Hybrid mock intelligence data layer v0.3.6 deployed. 9 tickers with company, fundamentals, ratios, earnings, targets, technical levels. IREN in positions, AVAV+TSLA in watchlist.
Runtime Governance | LOCKED 2026-05-28 (v0.3.15): Single Next Dev Server Rule — only one Next dev server may run; check port 3000 first; kill stale node/next/npm and delete frontend/.next before restart; start LAN-bound (npm run dev -- -H 0.0.0.0); never run npm run build against a live dev server's .next; unstyled mobile = suspect stale/corrupt .next (404 CSS chunk), not UI code.
Workspace Manager | IMPLEMENTED 2026-05-28 (v0.3.15): Mobile top-left hamburger opens Workspace Manager; bottom nav uses pia.workspaces.pinnedMobile capped at five; desktop sidebar uses pia.workspaces.sidebarDesktop; custom workspaces persist in pia.workspaces.custom; shared order persists in pia.workspaces.order.
Workspace Manager | IMPLEMENTED 2026-05-28 (v0.3.15): Mobile top-left hamburger opens Workspace Manager; Settings/About are accessible; all/overflow workspaces can open directly; bottom nav uses pia.workspaces.pinnedMobile capped at five; desktop sidebar uses pia.workspaces.sidebarDesktop; custom workspaces persist in pia.workspaces.custom; shared order persists in pia.workspaces.order.
Mobile Regression Fix | DONE 2026-05-28 (v0.3.16): Global search universe expanded (AAPL/MSFT/AMZN/META/SPY/QQQ/+ v0.3.6 set) with Enter-to-open and Analyze fallback; per-ticker mock news fallback (generate_mock_news) so every symbol shows source-badged news; used_demo only true for demo/mock, false for real Yahoo. Hamburger menu satisfied by v0.3.15 Workspace Manager.